## COVER
Charrette MG
Ralph Lauren — Town Center at Boca Raton
Preliminary open-book CM exhibit for Charrette review. Commercial terms as of 4 Sep 2026. Cost-plus CM + GC, open book. Yellow cells are commercial inputs. Confirmed: 21 weeks, 10% CM fee on sub/trade costs only (GC fees not marked up), 10% CO markup (one-or-the-other with CM — not stacked), 1.5% insurance, $4,400/wk superintendent, Shawn PM $3,500/wk + 4 trips, parking 5 mo × $250, pre-construction 1% first pay app / NTP. LBC opening payment ask: net 30 on monthly % complete (settlement band net 45; RL policy often net 90). Trade packages remain $0 until bids. Form rollups are GC/fee math only — not a bid total.
JOB IDENTITY
Client | Ralph Lauren
Location | Town Center at Boca Raton, Simon space 1062, 600 Glades Road
Area | 3,800 sf
Owner's representative | Charrette MG — Landis Kauffman, Claudia Mardones
Contract | Cost-plus / CM + GC (not lump sum)
Payment | LBC ask net 30 (monthly % complete) ¦ settlement band net 45 ¦ RL policy often net 90 ¦ Cost-plus CM open book
Calendar (intake) | Commence 2027-04-02 ¦ Substantial 2027-08-18 (~19.5 weeks intake calendar) ¦ Final 2027-08-25 ¦ Duration: 21 weeks (used on LANDIS FORM and superintendent weeks)
Architect | TPG
RL NDA | 2026-07-14
RL contact on drawings | dorit.alexander@ralphlauren.com
Permit fees | Excluded / invoiced separately
Sales tax | Invoiced separately
GC | LUX Brand Company
NOTES
Open book | This workbook is a preliminary open-book CM exhibit for Charrette review. Commercial terms as of 3 Sep 2026. It is not a lump-sum bid and not an awarded contract price. Pre-construction fee: 1% of project total, payable with the first application for payment / NTP.
Blank inputs | Filled yellow = confirmed as of 3 Sep 2026 (21 weeks, CM 10%, insurance 1.5%, weekly superintendent $4,400, pre-construction 1% with first application for payment / NTP). Remaining yellow is OPEN — to be confirmed. On-site laborer and project-manager week counts remain open. $0 trade rows and GC/fee subtotals are not a bid grand total.
Calendar vs duration | Intake calendar: commence 2027-04-02 through substantial 2027-08-18 (~19.5 weeks), final 2027-08-25. Duration used on LANDIS FORM and superintendent weeks is 21 weeks.
Permits / tax | Permit fees are excluded and invoiced separately. Sales tax is invoiced separately.
Trades | No trade-package dollars are entered. PROPOSED ROSTER is proposed, not awarded. Mall unit rates are listed on MALL FEES; parking months and sprinkler-shutdown count are OPEN — to be confirmed. Form rollups from weekly superintendent × 21 + % fees are GC/fee math only — not a job with bid trades.
Sheets | COVER ¦ GC BID FORM ¦ LANDIS FORM ¦ MALL FEES ¦ PROPOSED ROSTER

## LANDIS FORM
Ralph Lauren Boca Raton Town Center 1062 — CM Fee Budget Breakdown
LUX Brand Company ¦ Cost-plus CM + GC (open book, not lump sum) ¦ Town Center at Boca Raton, Simon space 1062, 600 Glades Road ¦ 3,800 sf
Owner's representative: Charrette MG — Landis Kauffman, Claudia Mardones. Payment: Ralph Lauren policy net 90. Permit fees excluded / invoiced separately. Sales tax invoiced separately.
Duration (weeks) — confirmed: 21
21 | Weeks (single duration input for this form) |  |  | Confirmed: 21 weeks. Intake calendar ~19.5 weeks (2027-04-02 to 2027-08-18) is recorded on COVER; it is not the duration used here.
COMMERCIAL INPUTS (yellow). Filled yellow = confirmed as of 4 Sep 2026. Trade package amounts stay $0 until bids.
| Item |  | Input | Status
| Pre-construction fee % of project total (dollar on D43) |  | 1% | Confirmed: 1% of project total, payable with the first application for payment / NTP. Dollar = E9 × (trades + weekly GC + CM fee + insurance). Trade packages are $0 until bids, so the current dollar is 1% of GC/fee/insurance only and will update when packages are bid.
| Weekly superintendent $ — multiplied by Weeks (B5) = General Conditions |  | 4400 | Confirmed: weekly superintendent $4,400. Used as the weekly GC & supervision input on this form. Shawn Rasmusen PM is Set at $3,500/wk + 4 trips (see COVER / GC BID FORM) — not included in this weekly superintendent line.
| CM Fee % of cost of work |  | 10% | Confirmed: 10% of sub/trade packages only (D20:D39). Does NOT apply to General Conditions (fees) or to insurance 1.5%. Dollar calculates when sub bid packages are in.
| Insurance % |  | 1.5% | Confirmed: 1.5% on total revenue nut (trades + General Conditions) — carrier prices on total revenue. NOT marked up by CM 10%. Workers compensation billed in payroll burden on GC BID FORM; not duplicated here. Dollar updates when sub bid packages are in.
| CO markup % (separate line-item — does NOT follow project CM fee) |  | 10% | Confirmed: 10% CO markup. Separate line-item — one-or-the-other with CM 10% (E12); NOT stacked on the same dollars. Does not follow project CM fee automatically.
| CO Insurance % (follows project insurance 1.5%) |  |  | Tracks E13 (confirmed 1.5%). This is insurance, not CO markup. CO markup % is E15 — confirmed 10% (one-or-the-other with CM).
TRADE PACKAGES — no bid packages received; amounts 0
# | Description | Amount
1 | Trade package 1 — bid not received | 0
2 | Trade package 2 — bid not received | 0
3 | Trade package 3 — bid not received | 0
4 | Trade package 4 — bid not received | 0
5 | Trade package 5 — bid not received | 0
6 | Trade package 6 — bid not received | 0
7 | Trade package 7 — bid not received | 0
8 | Trade package 8 — bid not received | 0
9 | Trade package 9 — bid not received | 0
10 | Trade package 10 — bid not received | 0
11 | Trade package 11 — bid not received | 0
12 | Trade package 12 — bid not received | 0
13 | Trade package 13 — bid not received | 0
14 | Trade package 14 — bid not received | 0
15 | Trade package 15 — bid not received | 0
16 | Trade package 16 — bid not received | 0
17 | Trade package 17 — bid not received | 0
18 | Trade package 18 — bid not received | 0
19 | Trade package 19 — bid not received | 0
20 | Trade package 20 — bid not received | 0
| General Conditions (Weekly GC × Weeks) |  |  | Confirmed: D40 = E11 × B5 = $4,400 × 21 = $92,400 weekly-GC subtotal. Not a job grand total. Laborer and project manager are not included in this weekly line.
| CM Fee (10% × sub/trade packages only — NOT on GC) |  |  | CM fee = 10% × trade packages only. Not on GC fees. Not on insurance. Trades $0 until bid — CM fee $0 until packages are bid.
| Insurance (1.5% × trades + GC — total revenue; NOT marked up by CM) |  |  | Insurance = 1.5% × (trade packages + General Conditions). Carrier basis = total revenue. CM 10% does not apply on top of this 1.5%. Real dollar once sub bids are in.
| Pre-construction fee (1% × trades + GC + CM fee + insurance) |  |  | Confirmed: payable with the first application for payment / NTP. 1% of the form subtotal (trades $0 + weekly GC + CM fee + insurance). Dollar will change when trade packages are bid.
FORM ROLLUP (GC / fee / pre-con only — trades $0; not a bid total) |  |  |  | Sum of trade rows ($0 until bid) + weekly GC × weeks + CM 10% + insurance 1.5% + pre-construction 1%. Not a lump-sum bid and not an awarded contract price.
Preliminary open-book exhibit for Charrette review. Confirmed as of 4 Sep 2026: B5 = 21 weeks, E11 = $4,400/wk superintendent, E12 = 10% CM on SUB costs only (not on GC fees; not on insurance), E13 = 1.5% insurance on total revenue (trades + GC; carrier method), E15 = 10% CO markup (one-or-the-other with CM — not stacked), E9 = 1% pre-construction payable with first pay app / NTP. Trade rows $0 until packages are bid — CM and insurance dollars update then.

## GC BID FORM
Charrette MG
BID SCHEDULE
Preliminary open-book exhibit for Charrette review
[5 empty] | Project Bid | USD |  | Rollup follows confirmed CM 10%, insurance 1.5%, superintendent $4,400 × 21, plus workers compensation 1.2% on payroll. Laborer and project-manager weeks, main-office overhead, warranty, and all trade / general-requirements dollars remain OPEN or $0. Not a lump-sum bid total.
[5 empty] | Total with Escrows | USD
| CONTRACT TYPE: | Cost-Plus CM (open book) |  |  | Add Alternates | USD | 0
| LABOR: | Non-Union |  |  | Deduct Alternates | USD | 0
| LOCATION: | Ralph Lauren Boca Raton — Town Center space 1062
| GC: | LUX Brand Company
CSI Code | Description | Notes |  |  |  | Unit | Costs & Fees | GC Notes
| ESCROWS, ALLOWANCES & REIMBURSABLES |  |  |  |  | Sub Total | 0
E1.0 | Special Insurances Required by Ralph Lauren |  |  |  |  | ALLOW | 0 | Standard GC insurance certificates. Additional special insurance if required by Ralph Lauren.
E2.0 | Performance Bond and/or Sureties |  |  |  |  | ALLOW | 0 | None required
E3.0 | Permits, Fees, Connection Costs, Access Fees, Landlord Fees |  |  |  |  | ALLOW | 0 | Permit fees excluded — to be invoiced separately
E4.0 | Contingency Account or At-Risk Account/Fee |  |  |  |  | ALLOW | 0 | None
E5.0 | Sales Tax (district, local, state) |  |  |  | Specify if included in subs | ALLOW | 0 | Sales tax invoiced separately per contract — not included
00 / 01 | PROCUREMENT & GENERAL REQUIREMENTS
A | OVERHEAD & PROFIT (OH&P) |  |  |  |  | Sub Total
A-1 | Overhead & Profit |  |  |  |  | 10% |  | Confirmed: 10% CM fee / OH&P of cost of work.
B | GENERAL CONTRACTOR OVERHEAD |  |  |  |  | Sub Total
B-2 | Main Office Overhead Rate (excl. project payroll) | [6 empty] | OPEN — to be confirmed
B-3 | Liability Insurance |  |  |  |  | 1.5% |  | Confirmed: 1.5% liability insurance (limits confirmed). Workers compensation billed in payroll burden (C-7, 1.2%); not duplicated in this insurance %.
B-4 | 12-Month Owner-Required Warranty | [6 empty] | OPEN — to be confirmed
C | GENERAL CONTRACTOR DEDICATED ON-SITE PAYROLL |  |  |  |  | Total
| Note: Employee gross pay (no employer markup; OH/payroll taxes/WC computed separately) |  |  |  |  | Employer Payroll OH | 0
CC | Payroll Subtotal (incl. WC) |  |  |  |  | Subtotal
|  | Rate $/wk |  | Weeks |  |  | Total
C-1 | On Site Laborer (full time) | 2000 | Per Week |  | Weeks | TOTAL |  | Proposed laborer rate. Week count OPEN — to be confirmed.
C-2 | On Site Laborer — Store Setup Support | 0 | Per Week | 0 | Weeks | TOTAL |  | Not used on this project.
C-3 | On Site Laborer (part time) | 0 | Per Week | 0 | Weeks | TOTAL
C-4 | Field Engineer | 0 | Per Week | 0 | Weeks | TOTAL
C-5 | Project Manager | 3500 | Per Week |  | Weeks | TOTAL |  | Proposed project-manager rate. Week count OPEN — to be confirmed.
C-6 | Superintendent | 4400 | Per Week | 21 | Weeks | TOTAL |  | Confirmed: weekly superintendent $4,400 × 21 weeks.
C-7 | Workers Compensation (% of payroll subtotal) | 1.2% | Rate |  | × Subtotal | TOTAL |  | Workers compensation 1.2% of on-site payroll (C-1 through C-6). WC billed in payroll burden; not duplicated in the 1.5% insurance %.
D | GENERAL REQUIREMENTS WORK |  |  |  |  | Total
[6 empty] | Mark-Up | 0
DD | [5 empty] | Sub Total | 0
D-1 | Materials, travel, supplies, small tools, and consumables |  |  |  |  | T&M / ALLOW | 0 | General conditions
D-2 | Construction documentation and submittals |  |  |  |  | T&M / ALLOW | 0
D-3 | Independent testing and inspecting services |  |  |  |  | T&M / ALLOW | 0 | All testing by others — see Add Alternates
D-4 | X-ray concrete slabs / GPR / exploratory items |  |  |  |  | T&M / ALLOW | 0 | Included in Div 03 80 00
D-5 | Temporary utilities |  |  |  |  | T&M / ALLOW | 0 | By Landlord
D-6 | Temporary storage / staging space |  |  |  |  | T&M / ALLOW | 0
D-7 | Field office expense / WiFi |  |  |  |  | T&M / ALLOW | 0
D-8 | Vehicular access, traffic control & parking |  |  |  |  | T&M / ALLOW | 0
D-9 | Roads and sidewalks, temporary |  |  |  |  | T&M / ALLOW | 0
D-10 | Temporary barriers, enclosures, barricades |  |  |  |  | T&M / ALLOW | 0 | Mall barricades by Landlord
D-11 | Temporary security |  |  |  |  | T&M / ALLOW | 0
D-12 | Temporary protective walkways |  |  |  |  | T&M / ALLOW | 0
D-13 | Temporary fencing |  |  |  |  | T&M / ALLOW | 0
D-14 | Temporary project signage |  |  |  |  | T&M / ALLOW | 0
D-15 | Equipment (cranes, hoists, lifts) |  |  |  |  | T&M / ALLOW | 0
D-16 | Field engineering / professional expenses / Permit Fees |  |  |  | Permit fees NOT included in this pricing | T&M / ALLOW | 0 | Permit fees excluded
D-17 | Progress cleaning and debris removal |  |  |  |  | T&M / ALLOW | 0 | Daily site cleanup by GC
D-18 | Final clean by GC at end of job |  |  |  |  | T&M / ALLOW | 0 | Two cleans — pre-handover and pre-opening
D-19 | Temporary protection, dust control, tarping |  |  |  |  | T&M / ALLOW | 0 | Floor protection and dust control
D-20 | Building commissioning, turnover, lien releases |  |  |  |  | T&M / ALLOW | 0
D-21 | Travel expense |  |  |  |  | T&M / ALLOW | 0 | OPEN — to be confirmed
D-22 | Mall non-refundable site fees |  |  |  | Sprinkler shut-down fees etc. | T&M / ALLOW | 0 | Listed mall unit rates (see MALL FEES): temp electric $1,455.12 + temp water $338.40 + after hours $400 + tenant coordination $250 = $2,443.52. This line stays $0 until entered as a bid dollar. Parking months and sprinkler-shutdown count are OPEN — to be confirmed. Mall figures are unit-rate notes, not a bid total.
HARD COST SUBTOTAL

## MALL FEES
Mall fees — unit rates on 3,800 sf (notes, not a job grand total)
LUX Brand Company ¦ Ralph Lauren ¦ Town Center at Boca Raton, Simon space 1062 ¦ Permit fees excluded / invoiced separately ¦ Sales tax invoiced separately
Area (sf) | 3800 | Area used only to extend $/sf mall items below
Item | Unit rate | Unit | Qty | Extension | Status | Notes
Temporary electric | 0.43 | $/sf | 3800 | 1455.12 | Listed | Unit rate $0.43/sf × 3,800 sf. Extension is rate × sf, not a job total.
Temporary water | 0.1 | $/sf | 3800 | 338.4 | Listed | Unit rate $0.10/sf × 3,800 sf. Extension is rate × sf, not a job total.
After hours | 400 | one-time | 1 | 400 | Listed | Unit rate $400 one-time.
Parking | 250 | $/month | 5 |  | Set | Unit rate $250/month. Month count OPEN — to be confirmed. Extension waits on E10.
Tenant coordination | 250 | one-time | 1 | 250 | Listed | Unit rate $250 one-time.
Sprinkler shutdown | 250 | each |  |  | OPEN | Unit rate $250 each. Count OPEN — to be confirmed. Extension waits on E12.
Permit fees | Excluded / invoiced separately. Not extended on this sheet.
Sales tax | Invoiced separately. Not extended on this sheet.
Listed mall dollars on this sheet (not a job grand total): temp electric $1,455.12 + temp water $338.40 + after hours $400 + tenant coordination $250 = $2,443.52. Parking months and sprinkler-shutdown count are OPEN — to be confirmed. Unit rates on 3,800 sf — not a bid total.

## PROPOSED ROSTER
Proposed roster (proposed, not awarded)
LUX Brand Company ¦ Ralph Lauren ¦ Town Center at Boca Raton, Simon space 1062 ¦ Names below are proposed only. No trade-package dollars on LANDIS FORM until bids are received.
Scope | Proposed firm | Status | Notes
Superintendent | Robert Colvin | Proposed | Not awarded.
Project Manager | Shawn Rasmusen | Set | $3,500/wk + 4 trips. Not in LANDIS FORM weekly superintendent line.
Demo | MSA Painting | Proposed | Not awarded.
Scan / cut | Big T | Proposed | Not awarded.
Framing / drywall | Hunt Interiors | Proposed | Not awarded.
Electrical | TBD — Alcor or South Palm | Proposed / TBD | Not awarded. Firm not selected.
Low voltage | TBD — Alcor or South Palm | Proposed / TBD | Same shortlist as electrical. Not awarded.
Plumbing | Langes | Proposed | Not awarded.
HVAC | Air South | Proposed | Not awarded.
Storefront | TBD — RSG or Abbott | Proposed / TBD | Not awarded. Firm not selected.
Flooring | Twins | Proposed | Not awarded.
Paint | National Retail Painting | Proposed | Not awarded.
Sprinklers | Polaris | Proposed (mall) | Mall-required. Not awarded.
Fire alarm | JCI | Proposed (mall) | Mall-required. Not awarded.
FA rough-in | South Palm | Proposed (mall) | Mall-required. Not awarded.
Roof | RSS if needed | Proposed (mall) | Mall. Only if needed. Not awarded.
Doors | TBD | Proposed / TBD | Firm not listed. Not awarded.
BOH millwork | Woodchuck | Proposed | Not awarded.
Carpentry | LBC | Proposed | LUX Brand Company carpentry. Not awarded as a trade package.
Final clean | Filthy Clean | Proposed | Not awarded.
Dumpsters | Coastal Waste | Proposed (mall) | Mall. Not awarded.
Proposed, not awarded. Trade-package dollars remain $0 until bids are received.