## COVER
LUX Brand Company
Ralph Lauren — Town Center at Boca Raton
Open-book cost-plus CM exhibit. Not a lump-sum bid.
Commercial terms: 21 weeks · $4,400/wk superintendent · $3,500/wk project manager (Shawn Rasmusen) + 4 trips · 5 months parking × $250 = $1,250 · 10% CM fee · 1.5% liability insurance · 1% pre-construction, payable with first pay application / NTP.
JOB IDENTITY
Client | Ralph Lauren
Location | Town Center at Boca Raton, Simon space 1062, 600 Glades Road
Area | 3,384 sf
Owner's representative | Charrette MG — Landis Kauffman, Claudia Mardones
Contract | Cost-plus / CM + GC (not lump sum)
Payment | Opening ask: net 30. If net 30 is not accepted, net 45 is a possible settlement band. Ralph Lauren stated policy: net 90.
Calendar (intake) | Commence 2027-04-02 ¦ Substantial 2027-08-18 ¦ Final 2027-08-25
Architect | TPG
RL NDA | 2026-07-14
RL contact on drawings | dorit.alexander@ralphlauren.com
Permit fees | Excluded / invoiced separately
Sales tax | Invoiced separately
GC | LUX Brand Company
Duration | 21 weeks

## GC BID FORM
BID SCHEDULE
Open-book cost-plus CM exhibit — not a lump-sum bid.
[5 empty] | Project Bid | USD |  | Rollup of entered lines. Trade packages not yet bid.
[5 empty] | Total with Escrows | USD
| CONTRACT TYPE: | Cost-Plus CM (open book) |  |  | Add Alternates | USD | 0
| LABOR: | Non-Union |  |  | Deduct Alternates | USD | 0
| LOCATION: | Ralph Lauren Boca Raton — Town Center space 1062
| GC: | LUX Brand Company
CSI Code | Description | Notes |  |  |  | Unit | Costs & Fees | GC Notes
| ESCROWS, ALLOWANCES & REIMBURSABLES |  |  |  |  | Sub Total | 0
E1.0 | Special Insurances Required by Ralph Lauren |  |  |  |  | ALLOW | 0 | Standard LBC certificates assumed adequate
E2.0 | Performance Bond and/or Sureties |  |  |  |  | ALLOW | 0 | None required
E3.0 | Permits, Fees, Connection Costs, Access Fees, Landlord Fees |  |  |  |  | ALLOW | 0 | Permit fees excluded — to be invoiced separately
E4.0 | Contingency Account or At-Risk Account/Fee |  |  |  |  | ALLOW | 0 | None
E5.0 | Sales Tax (district, local, state) |  |  |  | Specify if included in subs | ALLOW | 0 | Sales tax invoiced separately per contract — not included
00 / 01 | PROCUREMENT & GENERAL REQUIREMENTS
A | OVERHEAD & PROFIT (OH&P) |  |  |  |  | Sub Total
A-1 | Overhead & Profit |  |  |  |  | 10% |  | 10% CM / overhead & profit.
B | GENERAL CONTRACTOR OVERHEAD |  |  |  |  | Sub Total
B-2 | Main Office Overhead Rate (excl. project payroll) | [6 empty] | N/A — not used on this exhibit.
B-3 | Liability Insurance |  |  |  |  | 1.5% |  | 1.5% liability insurance. Workers' compensation 1.2% is row C-7.
B-4 | 12-Month Owner-Required Warranty
C | GENERAL CONTRACTOR DEDICATED ON-SITE PAYROLL |  |  |  |  | Total
| Note: Employee gross pay (no employer markup; OH/payroll taxes/WC computed separately) |  |  |  |  | Employer Payroll OH | 0
CC | Payroll Subtotal (incl. WC) |  |  |  |  | Subtotal
|  | Rate $/wk |  | Weeks |  |  | Total
C-1 | On Site Laborer (full time) | 2000 | Per Week |  | Weeks | TOTAL
C-2 | On Site Laborer — Store Setup Support | 0 | Per Week | 0 | Weeks | TOTAL |  | Not used on this project (zeroed).
C-3 | On Site Laborer (part time) | 0 | Per Week | 0 | Weeks | TOTAL
C-4 | Field Engineer | 0 | Per Week | 0 | Weeks | TOTAL
C-5 | Project Manager | 3500 | Per Week | 21 | Weeks | TOTAL |  | Shawn Rasmusen. $3,500 per week × 21 weeks + 4 trips.
C-6 | Superintendent | 4400 | Per Week | 21 | Weeks | TOTAL |  | $4,400 per week × 21 weeks.
C-7 | Workers Compensation (% of payroll subtotal) | 1.2% | Rate |  | × Subtotal | TOTAL |  | 1.2% of on-site payroll. Separate from B-3 liability insurance.
D | GENERAL REQUIREMENTS WORK |  |  |  |  | Total
[6 empty] | Mark-Up | 0
DD | [5 empty] | Sub Total | 0
D-1 | Materials, travel, supplies, small tools, and consumables |  |  |  |  | T&M / ALLOW | 0 | General conditions
D-2 | Construction documentation and submittals |  |  |  |  | T&M / ALLOW | 0
D-3 | Independent testing and inspecting services |  |  |  |  | T&M / ALLOW | 0 | All testing by others — see Add Alternates
D-4 | X-ray concrete slabs / GPR / exploratory items |  |  |  |  | T&M / ALLOW | 0 | Included in Div 03 80 00
D-5 | Temporary utilities |  |  |  |  | T&M / ALLOW | 0 | By Landlord
D-6 | Temporary storage / staging space |  |  |  |  | T&M / ALLOW | 0
D-7 | Field office expense / WiFi |  |  |  |  | T&M / ALLOW | 0
D-8 | Vehicular access, traffic control & parking |  |  |  |  | T&M / ALLOW | 0
D-9 | Roads and sidewalks, temporary |  |  |  |  | T&M / ALLOW | 0
D-10 | Temporary barriers, enclosures, barricades |  |  |  |  | T&M / ALLOW | 0 | Mall barricades by Landlord
D-11 | Temporary security |  |  |  |  | T&M / ALLOW | 0
D-12 | Temporary protective walkways |  |  |  |  | T&M / ALLOW | 0
D-13 | Temporary fencing |  |  |  |  | T&M / ALLOW | 0
D-14 | Temporary project signage |  |  |  |  | T&M / ALLOW | 0
D-15 | Equipment (cranes, hoists, lifts) |  |  |  |  | T&M / ALLOW | 0
D-16 | Field engineering / professional expenses / Permit Fees |  |  |  | Permit fees NOT included in this pricing | T&M / ALLOW | 0 | Permit fees excluded
D-17 | Progress cleaning and debris removal |  |  |  |  | T&M / ALLOW | 0 | Daily site cleanup by GC
D-18 | Final clean by GC at end of job |  |  |  |  | T&M / ALLOW | 0 | Two cleans — pre-handover and pre-opening
D-19 | Temporary protection, dust control, tarping |  |  |  |  | T&M / ALLOW | 0 | Floor protection and dust control
D-20 | Building commissioning, turnover, lien releases |  |  |  |  | T&M / ALLOW | 0
D-21 | Travel expense |  |  |  |  | T&M / ALLOW | 0
D-22 | Mall non-refundable site fees |  |  |  | Sprinkler shut-down fees etc. | T&M / ALLOW | 0 | Mall site-fee unit rates are on MALL FEES. Permit fees and sales tax invoiced separately.
HARD COST SUBTOTAL

## LANDIS FORM
Ralph Lauren Boca Raton Town Center 1062 — CM Fee Budget Breakdown
LUX Brand Company ¦ Cost-plus CM + GC (open book, not lump sum) ¦ Town Center at Boca Raton, Simon space 1062, 600 Glades Road ¦ 3,384 sf
Owner's representative: Charrette MG — Landis Kauffman, Claudia Mardones. Payment: opening ask net 30; net 45 is a possible settlement band if net 30 is not accepted (Ralph Lauren stated policy is net 90). Permit fees excluded / invoiced separately. Sales tax invoiced separately.
Duration (weeks)
21 | Weeks (single duration input for this form) |  |  | 21 weeks.
COMMERCIAL TERMS
| Item |  | Input | Status
| Pre-construction fee |  |  | 1% of project total, payable with first pay application / NTP.
| Weekly GC & supervision $ |  | 4400 | $4,400 per week superintendent. Project manager $3,500/wk (Shawn Rasmusen) + 4 trips — see GC bid form C-5.
| CM Fee % of cost of work |  | 10% | 10% of cost of work.
| Insurance % |  | 1.5% | 1.5% liability insurance. Workers' compensation is on the GC bid form payroll row.
| CO CM Fee % (open — separate from project CM fee) |  |  | Open — separate from the 10% project CM fee.
| CO Insurance % (follows project insurance) |  |  | Follows project insurance.
TRADE PACKAGES — TBD until bids are received (amounts stay blank for formula safety)
# | Description | Amount
1 | Trade package 1
2 | Trade package 2
3 | Trade package 3
4 | Trade package 4
5 | Trade package 5
6 | Trade package 6
7 | Trade package 7
8 | Trade package 8
9 | Trade package 9
10 | Trade package 10
11 | Trade package 11
12 | Trade package 12
13 | Trade package 13
14 | Trade package 14
15 | Trade package 15
16 | Trade package 16
17 | Trade package 17
18 | Trade package 18
19 | Trade package 19
20 | Trade package 20
| General Conditions (Weekly GC × Weeks) |  |  | Weekly superintendent × 21 weeks.
| CM Fee (fee % × (trades + GC dollars)) |  |  | 10% of trades plus general conditions.
| Insurance (ins % × (trades + GC dollars)) |  |  | 1.5% of trades plus general conditions.
FORM ROLLUP |  |  |  | Entered commercial terms. Trade-package rows are TBD until bids are received. Blank amounts do not invent a job total.
Cost-plus CM fee form. Duration 21 weeks. Superintendent $4,400/wk. Project manager $3,500/wk + 4 trips. Parking 5 months × $250 = $1,250. CM fee 10%. Insurance 1.5%. Pre-construction 1% of project total, payable with first pay application / NTP.

## MALL FEES
Mall fees — Town Center at Boca Raton, 3,384 sf
LUX Brand Company ¦ Ralph Lauren ¦ Town Center at Boca Raton, Simon space 1062 ¦ Permit fees excluded / invoiced separately ¦ Sales tax invoiced separately
Area (sf) | 3384 | Project area used to extend per-square-foot items
Item | Unit rate | Unit | Qty | Extension | Status | Notes
Temporary electric | 0.43 | $/sf | 3384 |  | Listed | $0.43/sf × 3,384 sf.
Temporary water | 0.1 | $/sf | 3384 |  | Listed | $0.10/sf × 3,384 sf.
After hours | 400 | one-time | 1 |  | Listed | $400 one-time.
Parking | 250 | $/month | 5 |  | Set — 5 months | $250 × 5 months = $1,250 (from 21-week duration).
Tenant coordination | 250 | one-time | 1 |  | Listed | $250 one-time.
Sprinkler shutdown | 250 | each |  |  | Qty pending | $250 each. Count to be confirmed.
Permit fees | Excluded / invoiced separately. Not extended on this sheet.
Sales tax | Invoiced separately. Not extended on this sheet.
Parking is set at 5 months × $250 = $1,250. Sprinkler-shutdown count still Open / TBD. Permit fees and sales tax invoiced separately.

## PROPOSED ROSTER
Proposed roster — proposed, not awarded
LUX Brand Company ¦ Ralph Lauren ¦ Town Center at Boca Raton, Simon space 1062 ¦ Names below are proposed only. Trade-package dollars are entered after bids are received.
Scope | Proposed firm | Status | Notes
Superintendent | Robert Colvin | Proposed | Proposed, not awarded.
Demo | MSA Painting | Proposed | Not awarded.
Scan / cut | Big T | Proposed | Not awarded.
Framing / drywall | Hunt Interiors | Proposed | Not awarded.
Electrical | TBD — Alcor or South Palm | Proposed / TBD | Not awarded. Firm not selected.
Low voltage | TBD — Alcor or South Palm | Proposed / TBD | Same shortlist as electrical. Not awarded.
Plumbing | Langes | Proposed | Not awarded.
HVAC | Air South | Proposed | Not awarded.
Storefront | TBD — RSG or Abbott | Proposed / TBD | Not awarded. Firm not selected.
Flooring | Twins | Proposed | Not awarded.
Paint | National Retail Painting | Proposed | Not awarded.
Sprinklers | Polaris | Proposed (mall) | Mall-required. Not awarded.
Fire alarm | JCI | Proposed (mall) | Mall-required. Not awarded.
FA rough-in | South Palm | Proposed (mall) | Mall-required. Not awarded.
Roof | RSS if needed | Proposed (mall) | Mall. Only if needed. Not awarded.
Doors | TBD | Proposed / TBD | Firm not listed. Not awarded.
BOH millwork | Woodchuck | Proposed | Not awarded.
Carpentry | LBC | Proposed | LUX Brand Company carpentry. Not awarded as a trade package.
Final clean | Filthy Clean | Proposed | Not awarded.
Dumpsters | Coastal Waste | Proposed (mall) | Mall. Not awarded.
Proposed, not awarded. Trade-package amounts are entered after bids are received.