## COVER
LUX Brand Company
Ralph Lauren — Town Center at Boca Raton
This is a first-draft open-book exhibit, not a lump-sum bid.
Cost-plus CM + GC. Yellow cells on the following sheets are commercial inputs still OPEN. No weeks, CM fee %, insurance %, weekly superintendent rate, or job grand total has been filled as a decided number.
JOB IDENTITY
Client | Ralph Lauren
Location | Town Center at Boca Raton, Simon space 1062, 600 Glades Road
Area | 3,384 sf
Owner's representative | Charrette MG — Landis Kauffman, Claudia Mardones
Contract | Cost-plus / CM + GC (not lump sum)
Payment | Ralph Lauren policy: net 90
Calendar (intake) | Commence 2027-04-02 ¦ Substantial 2027-08-18 (~19.5 weeks) ¦ Final 2027-08-25
Architect | TPG
RL NDA | 2026-07-14
RL contact on drawings | dorit.alexander@ralphlauren.com
Permit fees | Excluded / invoiced separately
Sales tax | Invoiced separately
GC | LUX Brand Company
NOTES
Open book | This workbook is a first-draft open-book CM exhibit for discussion with Charrette. It is not a lump-sum bid and not an awarded contract price.
Blank inputs | Weeks, CM fee %, insurance %, and weekly superintendent stay blank (yellow) until confirmed. Do not read $0 rollups on GC BID FORM or LANDIS FORM as a bid total.
Calendar vs duration | Intake calendar is commence 2027-04-02 through substantial 2027-08-18 (~19.5 weeks), final 2027-08-25. A leftover 13-week figure from a prior template is listed on OPEN ITEMS and is not used as the duration.
Permits / tax | Permit fees are excluded and invoiced separately. Sales tax is invoiced separately.
Trades | No trade-package dollars are entered. PROPOSED ROSTER is proposed, not awarded. Mall unit rates are listed on MALL FEES; parking months and sprinkler-shutdown count stay OPEN.
Sheets | COVER ¦ GC BID FORM ¦ LANDIS FORM ¦ OPEN ITEMS ¦ MALL FEES ¦ PROPOSED ROSTER

## GC BID FORM
BID SCHEDULE
First-draft open-book exhibit — not a lump-sum bid
[5 empty] | Project Bid | USD |  | OPEN — rollup follows blank commercial inputs. Not a lump-sum bid total.
[5 empty] | Total with Escrows | USD
| CONTRACT TYPE: | Cost-Plus CM (open book) |  |  | Add Alternates | USD | 0
| LABOR: | Non-Union |  |  | Deduct Alternates | USD | 0
| LOCATION: | Ralph Lauren Boca Raton — Town Center space 1062
| GC: | LUX Brand Company
CSI Code | Description | Notes |  |  |  | Unit | Costs & Fees | GC Notes
| ESCROWS, ALLOWANCES & REIMBURSABLES |  |  |  |  | Sub Total | 0
E1.0 | Special Insurances Required by Ralph Lauren |  |  |  |  | ALLOW | 0 | Standard LBC certificates assumed adequate
E2.0 | Performance Bond and/or Sureties |  |  |  |  | ALLOW | 0 | None required
E3.0 | Permits, Fees, Connection Costs, Access Fees, Landlord Fees |  |  |  |  | ALLOW | 0 | Permit fees excluded — to be invoiced separately
E4.0 | Contingency Account or At-Risk Account/Fee |  |  |  |  | ALLOW | 0 | None
E5.0 | Sales Tax (district, local, state) |  |  |  | Specify if included in subs | ALLOW | 0 | Sales tax invoiced separately per contract — not included
00 / 01 | PROCUREMENT & GENERAL REQUIREMENTS
A | OVERHEAD & PROFIT (OH&P) |  |  |  |  | Sub Total
A-1 | Overhead & Profit | [6 empty] | OPEN — CM fee / OH&P % not set.
B | GENERAL CONTRACTOR OVERHEAD |  |  |  |  | Sub Total
B-2 | Main Office Overhead Rate (excl. project payroll) | [6 empty] | OPEN — main-office OH % not set (template leftover was 1%).
B-3 | Liability Insurance | [6 empty] | OPEN — insurance % not set.
B-4 | 12-Month Owner-Required Warranty | [6 empty] | OPEN — warranty % not set (template leftover was 1%).
C | GENERAL CONTRACTOR DEDICATED ON-SITE PAYROLL |  |  |  |  | Total
| Note: Employee gross pay (no employer markup; OH/payroll taxes/WC computed separately) |  |  |  |  | Employer Payroll OH | 0
CC | Payroll Subtotal (incl. WC) |  |  |  |  | Subtotal
|  | Rate $/wk |  | Weeks |  |  | Total
C-1 | On Site Laborer (full time) | 2000 | Per Week |  | Weeks | TOTAL |  | OPEN — weeks not set. See OPEN ITEMS (duration).
C-2 | On Site Laborer — Store Setup Support | 0 | Per Week | 0 | Weeks | TOTAL |  | Not used on this project (zeroed).
C-3 | On Site Laborer (part time) | 0 | Per Week | 0 | Weeks | TOTAL
C-4 | Field Engineer | 0 | Per Week | 0 | Weeks | TOTAL
C-5 | Project Manager | 3500 | Per Week |  | Weeks | TOTAL |  | OPEN — weeks not set. PM trip vs weekly pricing is on OPEN ITEMS.
C-6 | Superintendent |  | Per Week |  | Weeks | TOTAL |  | OPEN — weekly super rate and weeks not set. See OPEN ITEMS.
C-7 | Workers Compensation (% of payroll subtotal) | 1.2% | Rate |  | × Subtotal | TOTAL
D | GENERAL REQUIREMENTS WORK |  |  |  |  | Total
[6 empty] | Mark-Up | 0
DD | [5 empty] | Sub Total | 0
D-1 | Materials, travel, supplies, small tools, and consumables |  |  |  |  | T&M / ALLOW | 0 | General conditions
D-2 | Construction documentation and submittals |  |  |  |  | T&M / ALLOW | 0
D-3 | Independent testing and inspecting services |  |  |  |  | T&M / ALLOW | 0 | All testing by others — see Add Alternates
D-4 | X-ray concrete slabs / GPR / exploratory items |  |  |  |  | T&M / ALLOW | 0 | Included in Div 03 80 00
D-5 | Temporary utilities |  |  |  |  | T&M / ALLOW | 0 | By Landlord
D-6 | Temporary storage / staging space |  |  |  |  | T&M / ALLOW | 0
D-7 | Field office expense / WiFi |  |  |  |  | T&M / ALLOW | 0
D-8 | Vehicular access, traffic control & parking |  |  |  |  | T&M / ALLOW | 0
D-9 | Roads and sidewalks, temporary |  |  |  |  | T&M / ALLOW | 0
D-10 | Temporary barriers, enclosures, barricades |  |  |  |  | T&M / ALLOW | 0 | Mall barricades by Landlord
D-11 | Temporary security |  |  |  |  | T&M / ALLOW | 0
D-12 | Temporary protective walkways |  |  |  |  | T&M / ALLOW | 0
D-13 | Temporary fencing |  |  |  |  | T&M / ALLOW | 0
D-14 | Temporary project signage |  |  |  |  | T&M / ALLOW | 0
D-15 | Equipment (cranes, hoists, lifts) |  |  |  |  | T&M / ALLOW | 0
D-16 | Field engineering / professional expenses / Permit Fees |  |  |  | Permit fees NOT included in this pricing | T&M / ALLOW | 0 | Permit fees excluded
D-17 | Progress cleaning and debris removal |  |  |  |  | T&M / ALLOW | 0 | Daily site cleanup by GC
D-18 | Final clean by GC at end of job |  |  |  |  | T&M / ALLOW | 0 | Two cleans — pre-handover and pre-opening
D-19 | Temporary protection, dust control, tarping |  |  |  |  | T&M / ALLOW | 0 | Floor protection and dust control
D-20 | Building commissioning, turnover, lien releases |  |  |  |  | T&M / ALLOW | 0
D-21 | Travel expense |  |  |  |  | T&M / ALLOW | 0 | OPEN — PM travel/trips not confirmed. See OPEN ITEMS.
D-22 | Mall non-refundable site fees |  |  |  | Sprinkler shut-down fees etc. | T&M / ALLOW | 0 | Mall non-refundable site fees — unit rates on MALL FEES (not entered as dollars here). Permit fees excluded / invoiced separately. Sales tax invoiced separately.
HARD COST SUBTOTAL

## LANDIS FORM
Ralph Lauren Boca Raton Town Center 1062 — CM Fee Budget Breakdown
LUX Brand Company ¦ Cost-plus CM + GC (open book, not lump sum) ¦ Town Center at Boca Raton, Simon space 1062, 600 Glades Road ¦ 3,384 sf
Owner's representative: Charrette MG — Landis Kauffman, Claudia Mardones. Payment: Ralph Lauren policy net 90. Permit fees excluded / invoiced separately. Sales tax invoiced separately.
Duration (weeks) — OPEN, not filled
| Weeks (single duration input for this form) |  |  | OPEN — leftover 13 weeks not copied. Calendar ~19.5 weeks is on COVER / OPEN ITEMS, not entered here.
COMMERCIAL INPUTS (yellow) — blank until confirmed. Leftover template % not copied.
| Item |  | Input | Status
| Pre-construction fee $ |  |  | OPEN — not set.
| Weekly GC & supervision $ — multiplied by Weeks (B5) when both are filled |  |  | OPEN — weekly GC not set. Super $4,300 / $5,800 not copied.
| CM Fee % of cost of work |  |  | OPEN — leftover 10% not copied.
| Insurance % |  |  | OPEN — leftover 1.5% and Shawn 2%? not copied.
| CO CM Fee % (follows project CM fee) |  |  | Tracks E12. Stays empty/0 while E12 is OPEN.
| CO Insurance % (follows project insurance) |  |  | Tracks E13. Stays empty/0 while E13 is OPEN.
TRADE PACKAGES — no bid packages received; amounts 0
# | Description | Amount
1 | Trade package 1 — bid not received | 0
2 | Trade package 2 — bid not received | 0
3 | Trade package 3 — bid not received | 0
4 | Trade package 4 — bid not received | 0
5 | Trade package 5 — bid not received | 0
6 | Trade package 6 — bid not received | 0
7 | Trade package 7 — bid not received | 0
8 | Trade package 8 — bid not received | 0
9 | Trade package 9 — bid not received | 0
10 | Trade package 10 — bid not received | 0
11 | Trade package 11 — bid not received | 0
12 | Trade package 12 — bid not received | 0
13 | Trade package 13 — bid not received | 0
14 | Trade package 14 — bid not received | 0
15 | Trade package 15 — bid not received | 0
16 | Trade package 16 — bid not received | 0
17 | Trade package 17 — bid not received | 0
18 | Trade package 18 — bid not received | 0
19 | Trade package 19 — bid not received | 0
20 | Trade package 20 — bid not received | 0
| General Conditions (Weekly GC × Weeks) |  |  | Returns 0 while E11 or B5 is OPEN. Not a decided GC dollar.
| CM Fee (fee % × (trades + GC dollars)) |  |  | 0 until E12 is set. Leftover 10% not used.
| Insurance (ins % × (trades + GC dollars)) |  |  | 0 until E13 is set. Leftover 1.5% / 2%? not used.
FORM ROLLUP (not a lump-sum bid) |  |  |  | OPEN inputs → this rollup is $0. Not a job grand total.
Landis-shaped fee form for this cost-plus exhibit. Commercial inputs B5, E9, E11, E12, E13 are blank on purpose. Leftover 10% OH&P, 1.5% insurance, 1% main-office OH, 13 weeks, and super $4,300 / $5,800 are not entered. Trade rows stay $0 until packages are bid. See OPEN ITEMS, MALL FEES, and PROPOSED ROSTER.

## OPEN ITEMS
OPEN ITEMS — first-draft exhibit; leftover figures are not decided numbers
Yellow commercial inputs on GC BID FORM and LANDIS FORM stay blank until these items are closed. Leftover figures below are from a prior template or an internal 8/21 note — they are not copied as bid values.
# | Item | Leftover figure (if any) | Status | Owner
1 | Duration (weeks) | Leftover 13 weeks (prior Landis / super row) vs intake calendar 2027-04-02 to 2027-08-18 (~19.5 weeks). Mixed leftover payroll weeks on the old sheet were 24 / 7 / 13. None entered. | OPEN | Luke / Landis
2 | Superintendent weekly rate | Leftover GC sheet $5,800/wk vs Shawn 8/21 $4,300/wk. Neither copied onto E49 or Landis E11. | OPEN | Shawn
3 | CM fee / OH&P % | Leftover 10% on prior GC A-1 vs Landis E12 blank. 10% not copied. | OPEN | Luke
4 | Insurance % | Leftover 1.5% on prior GC B-3 vs Shawn 8/21 note 2%?. Neither copied onto I37 or Landis E13. | OPEN | Shawn
5 | PM trips / PM pricing | Shawn 8/21: 4 trips × $1,500? (question mark). Prior sheet leftover $3,500/wk × 7 weeks. Weeks blank; trip price not entered as a decided number. | OPEN | Shawn
6 | Main-office OH % | Leftover 1% template on prior GC B-2. Not copied onto I36. | OPEN | Luke
Color: yellow = OPEN. Owner is the person to close the item (Luke / Shawn / Landis). Calendar dates on COVER are intake facts, not a filled duration cell.

## MALL FEES
Mall fees — Shawn listed unit rates on 3,384 sf (not a job grand total)
LUX Brand Company ¦ Ralph Lauren ¦ Town Center at Boca Raton, Simon space 1062 ¦ Permit fees excluded / invoiced separately ¦ Sales tax invoiced separately
Area (sf) | 3384 | Shawn listed sf — used only to extend $/sf mall items below
Item | Unit rate | Unit | Qty | Extension | Status | Notes
Temporary electric | 0.43 | $/sf | 3384 |  | Listed | Shawn listed $0.43/sf × 3,384 sf. Extension is rate × sf, not a job total.
Temporary water | 0.1 | $/sf | 3384 |  | Listed | Shawn listed $0.10/sf × 3,384 sf. Extension is rate × sf, not a job total.
After hours | 400 | one-time | 1 |  | Listed | Shawn listed $400 one-time.
Parking | 250 | $/month |  |  | OPEN | Shawn listed $250/mo. Month count not filled (do not invent from calendar weeks).
Tenant coordination | 250 | one-time | 1 |  | Listed | Shawn listed $250 one-time.
Sprinkler shutdown | 250 | each |  |  | OPEN | Shawn listed $250 each. Count not filled.
Permit fees | Excluded / invoiced separately. Not extended on this sheet.
Sales tax | Invoiced separately. Not extended on this sheet.
No job grand total is shown. Parking months and sprinkler-shutdown count stay OPEN. GC BID FORM D-22 (J76) remains $0 until mall fees are confirmed and entered. Green extensions are listed-rate × known qty only.

## PROPOSED ROSTER
Proposed roster — Shawn 8/21 (proposed, not awarded)
LUX Brand Company ¦ Ralph Lauren ¦ Town Center at Boca Raton, Simon space 1062 ¦ Names below are proposed only. No trade-package dollars on LANDIS FORM until bids are received.
Scope | Proposed firm | Status | Notes
Superintendent | Robert Colvin | Proposed | Not awarded.
Demo | MSA Painting | Proposed | Not awarded.
Scan / cut | Big T | Proposed | Not awarded.
Framing / drywall | Hunt Interiors | Proposed | Not awarded.
Electrical | TBD — Alcor or South Palm | Proposed / TBD | Not awarded. Firm not selected.
Low voltage | TBD — Alcor or South Palm | Proposed / TBD | Same shortlist as electrical. Not awarded.
Plumbing | Langes | Proposed | Not awarded.
HVAC | Air South | Proposed | Not awarded.
Storefront | TBD — RSG or Abbott | Proposed / TBD | Not awarded. Firm not selected.
Flooring | Twins | Proposed | Not awarded.
Paint | National Retail Painting | Proposed | Not awarded.
Sprinklers | Polaris | Proposed (mall) | Mall-required. Not awarded.
Fire alarm | JCI | Proposed (mall) | Mall-required. Not awarded.
FA rough-in | South Palm | Proposed (mall) | Mall-required. Not awarded.
Roof | RSS if needed | Proposed (mall) | Mall. Only if needed. Not awarded.
Doors | TBD | Proposed / TBD | Firm not listed. Not awarded.
BOH millwork | Woodchuck | Proposed | Not awarded.
Carpentry | LBC | Proposed | LUX Brand Company carpentry. Not awarded as a trade package.
Final clean | Filthy Clean | Proposed | Not awarded.
Dumpsters | Coastal Waste | Proposed (mall) | Mall. Not awarded.
Proposed, not awarded. No CSI trade dollars were invented for this roster. LANDIS FORM trade rows remain $0.