## BID FORM
PROJECT: | Celine at Aventura | PROJECT SIZE: | 4015 SF
DRAWING MANIFEST: | Bid Set | DWG DATE: | 04/09/2026 - Permit Revision 1
GENERAL CONTRACTOR: | Lux Brand Company | LABOR TYPE: | NON UNION
|  | BID DUE DATE | 2026-01-09 | Revised 4/21/26
Notes
All breakout numbers and Alternates are required upon submission of bid.
GC must consult all LL-provided documentation, particularly with regards to work site security & badging and approved subcontractors
GC must provide cost per sqft / linear ft where applicable
GC to provide subsequent sheet with detailed description for each fee provided
All Millwork to be installed by millwork installer. GC to coordinate as needed
All items listed are for GC to FURNISH & INSTALL unless noted otherwise
Scope includes but is not limited to line item descriptions. Refer to plans for additional information
BID BREAK DOWN
|  | QTY | UNIT | RATE | TOTAL
01 _ General Requirements |  |  |  |  | 63555
| Barricade installation and Removal + Coordination of installation of Barricade Graphic (include making good LL finishes including LL tiles, transitions and finishes) - Touch up finishes after barricade is removed and Barricade rental. Barricade graphics are to be supplied by Celine |  |  |  | 13583
| Daily Site Cleaning |  |  |  | 0 | LBC holds each sub to daily cleaning before they leave so this is covered in the bid
| Final Site Cleans (3 MIN PROFESSIONAL REQUIRED) |  |  |  | 7830 | Stripping and waxing of BOH VCT areas now included
| Building Permit and Fees |  |  |  | 10000 | Allowance - Additionl permit fees above allowance will be a pass through expense at no markup
| Temporary Utilities |  |  |  | 0
| Project Documents and Controls |  |  |  | 3950
| (9) Dumpsters and Waste Removal (including millwork debris and crates) - No dumpsters provide for store stocking to comply with Building Rules and Regulations |  |  |  | 6500
| Coordination, receipt and storage of all Owner Furnished Items |  |  |  | 6425
| Floor Protection (including Masonite to protect finish floor) |  |  |  | 4730
| Production of shop drawings including revision for approval |  |  |  | 2800
| Inspection and Coordination |  |  |  | 3862
| Commissioning and Testing |  |  |  | 3875
| UL listing for Millwork and Exterior Signage with sticker |  |  |  | 0 | UL Listing of exterior signage included below, Millwork UL included in Division 18 below
| Samples as required |  |  |  | 0 | Samples including level 5 drywall finish are included
02 _ Site Construction |  |  |  |  | 5785
| Demolition ( include and specify night if required) |  |  |  | 5785 | Field review of landlord demolition requirerd to verify space at handover to GC. Added cost for demo per revision 6/Permit revision #1 4/9/26
03 _ Concrete |  |  |  |  | 55666
| Scanning and Investigations |  |  |  | 2400
| Grinding for floor Finishes |  |  |  | 0
| Saw cutting for all Trades |  |  |  | 13845
| Floor Trenching and Patching |  |  |  | 6750
| Floor Levelling of Existing floor up to 3/4" |  |  |  | 24600
| Vapor Barrier and Water Proofing Membrane |  |  |  | 3271
| Anti Fracture Membrane |  |  |  | 4800
04 _ Masonry |  |  |  |  | 64351
| Stone Supplied by Owner and Installed by GC |  |  |  | 48000
| Stone Storage by GC. Stone delivery to site by GC |  |  |  | 7325 | Revised per request from Celine - Storage and Receiving
| Drylay required for 20 tiles Maximum |  |  |  | 500
| FLOOR: Basaltite- 1197mmx11587mm Basaltina Marble Floor Tiles; |  |  |  | 3734 | Install for Landlord attic stock tile listed below
| Land Lord attic stock tile or stone - Assumes 162 SQFT and $34.00/SQFT for Material |  |  |  | 4792 | Supply of Landlord attic stock tile - 4 courses of tile
05_ Metals |  |  |  |  | 19185
| Structural Steel |  |  |  | 0
| Metal Decking |  |  |  | 0
| Metal Fabrications ( stairs, Railing, etc.) |  |  |  | 0
| Storefront metal framing and connections - cost must be broken down for storefront |  |  |  | 19185
| Structural metal work, beams post, bracing and Fasteners |  |  |  | 0
| Non structural metals |  |  |  | 0
| Misc. Metals |  |  |  | 0
| Storefront Structural Steel Framing |  |  |  | 0
| Other (please specify) |  |  |  | 0
06_ Wood and Plastic |  |  |  |  | 46220
| Rough Carpentry , Blocking , and Back Framing |  |  |  | 0 | Included in framing number below and breakout numbers below
| Plywood sheathing for Millwork installation |  |  |  | 3685
| Plywood Sheathing for Storefront (cost must be broken down) |  |  |  | 5875
| Finish Carpentry |  |  |  | 0
| Millwork _ BOH |  |  |  | 36660
| Other (please specify) |  |  |  | 0
07_ Thermal and Moisture Protection |  |  |  |  | 13550
| Waterproofing |  |  |  | 0
| Insulation |  |  |  | 0
| Roofing |  |  |  | 7875 | Materials decreased and no real change on labor for 2 holes versus 3
| Firestopping (Repair existing fireproofing at strutural columns) |  |  |  | 4750
| Caulking and Sealing (touch up fire caluking at exisitng demising walls) |  |  |  | 925
| Other (please specify) |  |  |  | 0
08_ Door and Windows |  |  |  |  | 204290
STOREFRONT WORK BY GENERAL CONTRACTOR
| Entrance doors and vestibule (Entrance doors by MWC per drawings) |  |  |  | 0
| Hardware set for Entrance Doors (By MWC per drawings) |  |  |  | 0
| Storefront system (Includes Glazing, Mullions, and Install) |  |  |  | 194895 | Entry doors included in pricing
| Storefront Glazing |  |  |  | 0
| Storefront Mullions |  |  |  | 0
| Storefront Cladding |  |  |  | 0
| Storefront Install |  |  |  | 0
| Storefront Shop Drawings |  |  |  | 0
| Storefront Engineering |  |  |  | 0
| GC to Coordinate Owner Vendor for Storefront Stone Installation |  |  |  | 0
0
| Internal Doors supply and Install |  |  |  | 0
| Internal Doors Hardware and Lockset Supply and Install (Door #08 and Door to unusable space) |  |  |  | 9395 | 5 point electrified lock included in pricing
09_ Finishes |  |  |  |  | 136665
| Drywall (wall type finishes) - Walls and Ceilings |  |  |  | 75015 | Level 5 finish mock up requested by Celine - Included in price and confrimed by subcontractor
| Ceiling Drywall |  |  |  | 35755 | Added drywall ceiling and framing in new BOH room per revised drawings
| ACT Ceiling |  |  |  | 5575 | Added ACT per revised drawings
| Vinyl flooring |  |  |  | 9225 | VCT Floor quoted not sheet goods
| Vinyl Base |  |  |  | 1325
| Painting (Level 5 Finish on Sales Floor - walls, ceiling & ceiling coves) - Includes BOH walls and ceilings |  |  |  | 9770
| Misc.: [M-1] Polished Stainless Steel Base - Install in areas not on sales floor |  |  |  | 0
| PT-1 Wall Finish |  |  |  | 0
| Stone flooring |  |  |  | 0
| Other (please specify) |  |  |  | 0
10_ Specialties |  |  |  |  | 16912
| Sign Permits including UL listing fees |  |  |  | 3500
| Logo installation (Sign Install - Sign supply by MWC) |  |  |  | 11250
| Lockers: Coordination of Owner Vendor Installation |  |  |  | 0
| Storage Shelving: Coordination of Owner Vendor Installation |  |  |  | 0
| Fire extinguishers and cabinets |  |  |  | 1875
| Supply and install of Braille and Tactile signage |  |  |  | 287
| Bathroom Accessories |  |  |  | 0
| Restroom Toilet Paper Holder |  |  |  | 0
| Restroom Flush Actuator Plate |  |  |  | 0
| Restroom Straight Grab Bar |  |  |  | 0
| Restroom Coat Hook |  |  |  | 0
| Restroom Mirrors |  |  |  | 0
0
11_ Equipment |  |  |  |  | 3185
Kitchen appliances supply and installation
| Refrigerator |  |  |  | 1600
| Dishwasher |  |  |  | 850
| Microwave |  |  |  | 360
| Water Machine |  |  |  | 0
| Safe _ Coordination and Installation of Owner Supplied |  |  |  | 375
12_ Furnishing |  |  |  |  | 0
| NOT USED |  |  |  | 0
14_ Conveying Systems |  |  |  |  | 0
| NOT USED |  |  |  | 0
0
0
15_ Fire Suppression |  |  |  |  | 31635
| Sprinkler systems |  |  |  | 26600 | Includes 3 additional sprinkler heads with 5' long branch pipe
| Sprinkler permits and Fees |  |  |  | 875
| Sprinkler Testing and Commissioning |  |  |  | 0
| Sprinkler shut down (4 shutdowns included) |  |  |  | 2000
| Shop drawings and Coordination up to 3 revisions |  |  |  | 1200
| Color match heads |  |  |  | 960
16 _ Plumbing |  |  |  |  | 23345
| Plumbing Fixtures and Equipment : Supply And Install |  |  |  | 21575 | Added second trip and materials to install dishwasher after C/O
Pantry Sink
Service Sink + Faucet
Drinking Fountain
Floor Drains
| Water Meter |  |  |  | 0 | Included in plumbing number above
| Plumbing permit and Fees |  |  |  | 570
| Other - Camera locate for plumbing tie-ins |  |  |  | 1200
17 _ Heating Ventilating and Air- Conditioning |  |  |  |  | 117275
| HVAC Equipment ( including F&I of dampers, sensors, control systems, heaters, exhaust fans etc. ) ALL COST TO BE INCLUDED, GC TO PROVIDE SPECIAL PRICING ON ITEMS IF REQUIRED |  |  |  | 111875 | Reduced per plan revisions 4/9/26
| Diffusers and Grills - specify lead time |  |  |  | 0
| HVAC Ductwork and Distribution |  |  |  | 0
| HVAC Permit and Fees |  |  |  | 3600
| Testing and Comissions | CONTROLS? |  |  | 0
| Air Balance report |  |  |  | 1800
| Shop drawings and Coordination up to 3 revisions |  |  |  | 0
18 _ Electric |  |  |  |  | 145801
| Electrical distributions |  |  |  | 92165 | ADT Rack, IT Rack, and Patch Panels by Owners Vendor
| Electrical Cabling and Conduits |  |  |  | 0
| Light switches, rectacaples,power and data outlets and finish plates (Included in above number) |  |  |  | 0
| Electrical : Equipment (batteries, inverters , etc.) |  |  |  | 6775
| Lighting at FOH (Install Owner Supplied) (Included in above number) |  |  |  | 0
| Lighting at BOH (Furnish and Install by GC) (Included in above number) |  |  |  | 0
| ELECTRICAL Lighting drivers; Furnish and Install ALL in scope of work (131 drivers includes 6 spares) |  |  |  | 6821
| ELECTRICAL Furnish and Install: Tele-data, WAPS (pull wires only), Floor Boxes, (Included in above number) |  |  |  | 0
| ELECTRICAL CCTV - wires supplied by owners vendor, GC to pull, termination by vendor (Included in above number) |  |  |  | 0
| ELECTRICAL AV - speaker and wire supplied by owner's vendor, GC to install speaker and pull wire, termination by vendor (Included in above number) |  |  |  | 0
| Shopper tracker_ Cabling by GC (termination by owner vendor ) (Included in above number) |  |  |  | 0
| EAS_ Cabling by GC (termination by vendor) coordination by GC (Included in above number) |  |  |  | 0
| Electrical driver labeling (coordination by GC) |  |  |  | 200
| Electrical permit and fees |  |  |  | 790
| Electrical testing and commissioning (Intertek UL Certification) |  |  |  | 13480 | UL Certification of low voltage lighting installed in millwork fixtures
| Smart meter_ Provided by owner vendor installed by GC |  |  |  | 0 | Install included in Electrical cost above, supply of smart meter by Owners Vendor
| Fire Alarm (Includes putting the system in test during install) |  |  |  | 24895
Shop drawings and Coordination up to 3 revisions (Included in fire alarm pricing above)
| Permits and Fees for Fire Alarm |  |  |  | 675
SUBTOTAL |  |  |  |  | 947420
GENERAL CONTRACTOR COSTS |  |  |  |  | 317112.6
010000 | General Conditions to include:
| Project Executive |  |  |  | 0
| Project Manager | Weeks | 15 | 3200 | 48000
| Site Super | Weeks | 25 | 3950 | 98750
| Site Laborer |  | 4@2000 | 4@4000 | 24000
| Field Staff Expenses (travel lodging, reimbursables) |  | 7 visits | 1350 | 9450
| Operational and head office cost |  |  |  | 13748
| Other (please specify) |  |  |  | 0
TAXES
OVERHEAD and FEE |  | Markup | 11.5% | 108953.3 | 108953.3
INSURANCE |  |  | 0.015 |  | 14211.3
GRAND TOTAL |  |  |  |  | 1264532.6 | This proposal excludes all governmental taxes, development charges, impact fees, utility fees, and other jurisdictional assessments unless specifically noted otherwise.
OTHER MISCELLANEOUS
| % on Change orders, incl. insurance |  | 11.5% |  | 11.5%
| Additional week of General Conditions |  | 9200 |  | 9200
| Supervision for Saturday During Millwork Installation |  | Inc. |  | 790 | Per Day of Saturday Millwork install supervision
| Add Alternate - Security mesh at corridor demising wall |  |  |  | 27275